## Cover
Project Title | Marketview app Migration to Azure
Customer Name | xyz
Primary Customer Contact | joe.m@xyz.com
Opportunity ID | PO-5683486
Application's Name | Marketview

## Stake Holders
Role | Name | Email ID | Organization
Manager, Sales |  |  | Cloud Sols
Manager, Pre-Sales |  |  | Cloud Sols
Project Manager | Senthil |  | Cloud Sols
Technical Solution Architect | Shiv |  | Cloud Sols
Sytem Engineer | Gowtham |  | Cloud Sols
Delivery Engineer | Sudharsan |  | Cloud Sols
Application Team | Shan | shan@xyz.com | Customer
Network Team | Mike |  | Customer
Virtualization\Infra Team | Russ |  | Customer
DB Team | Gilbert |  | Customer
Security Team | Robert |  | Customer

## Schedule
Activities | Weeks starting from delivery
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Week X
PLANNING & DESIGN (PRE-DELIVERY)
Share pre-requisite | [13 empty] | Planning
Create project plan | [13 empty] | In-progress
Discuss & Finalize deployment Strategy | [13 empty] | Pending
Shared deployment plan | [13 empty] | Complete
Validate pre-requisites/Readyness
INFRA SETUP (POST DELIVERY)
BOM Verfication
Azure account setup
Azure Network
Azure VMs
Azure DB
Azure Security
Config
Wave-1
On-prem to Azure VPN
Integrate DB & Application
Wave-2
Dev Infra Testing
App availability
Wave-3
Move app to PROD
Wave-4
Wave-5
Sing-Off

## Project Plan
No. | Task Name | Owner | Start | Finish | Comments
1 | Customer kick-off call |  | Sun 8/15/21
2 | Initial discussion with customer management |  | Sun 8/22/21
3 | On-prem Infra Discovery
4 | Discussion with customer tech team (App,DB,NW,Sec)
5 | Planning and Design Phase
6 | Deployment Project Plan

## Questionnaire
Dimension | Survey Question | Question Level | App Name 1 | App Name 2 | App Name 3 | App Name 4 | App Name 5 | App Name 6 | App Name 7 | App Name 8 | App Name 9 | App Name 10 | App Name 11 | App Name 12 | App Name 13 | App Name 14 | App Name 15 | App Name 16 | App Name 17 | App Name 18 | App Name 19 | App Name 20 | App Name 21 | App Name 22 | App Name 23 | App Name 24 | App Name 25 | App Name 26 | App Name 27 | App Name 28 | App Name 29 | App Name 30 | App Name 31 | App Name 32 | App Name 33 | App Name 34 | App Name 35 | App Name 36 | App Name 37 | App Name 38 | App Name 39 | App Name 40 | App Name 41 | App Name 42 | App Name 43 | App Name 44 | App Name 45 | App Name 46 | App Name 47 | App Name 48 | App Name 49 | App Name 50
STEP 1: Cloud readiness analysis
General | Application Unique ID (Refer: CI from CMDB) |  | Marketview
Application Functionality (Describe the app)
App Life expectancy (Decommisioning Time)
#REF!
| Compliance requirements (PCI DSS, FISMA, SOC, or "Others") | Enter
| If "Multiple", Please specify | Info
| If "Multiple", cloud suitability? | Rate
| Regulatory requirements - (Limiting data hosting to specific geography) | Enter
| If Yes for Regulatory, please indicate the limitation | Info
| If Yes for Regulatory, cloud suitability? | Rate
#REF!
| Application Type | Enter
| If "Others", Please specify | Info
| If "Others", cloud suitability? | Rate
| Technology Stack | Enter
| If "Others", Please specify | Info
| If "Others", cloud suitability? | Rate
| Operating System | Enter
| If "Others", Please specify | Info
| If "Others", cloud suitability? | Rate
#REF!
| Hardware Platform | Enter
| If Physical, platform details | Info
| If Physical, P2V feasible? | Rate
| Hardware / OS dependencies | Enter
| Dependency details | Info
| If there are Hardware/OS dependencies, cloud suitablity? | Rate
#REF!
| Licensing Limitations for Portability | Enter
| Limitation details | Info
| If Portability limitaions, cloud suitablity? | Rate
STEP 2: Cloud migration viability
#REF!
| Operating System | Enter
| If Others, please specify | Info
| Cloud suitabilty? | Rate
| Hardware Platform | Enter
| If not virtual, please provide platform details | Info
| If Physical, P2V feasible? | Rate
| Expected Data Bandwidth requirements | Enter
| Expected Latency requirements | Enter
#REF!
| Number of Integration Points | Enter
| List Upstream Dependencies (Application Names) | Info
| Upstream Dependencies | Enter
| List Downstream Dependencies (Application Names) | Info
| Dowstream Dependencies | Enter
#REF!
| Business Criticality | Enter
| Application Availability | Enter
#REF!
| Security Requirement | Enter
| In-transit Data Encryption | Enter
| If yes, Encryption details | Info
| Cloud suitabilty? | Rate
| Rest Data Encryption | Enter
| If yes, Encryption details | Info
| Cloud suitabilty? | Rate
| Authorization and Authentication Model | Enter
| If Others, please specify | Info
| Cloud suitabilty? | Rate
#REF!
| Database Management System (DBMS) | Enter
| DBMS Version Details | Info
| DBMS version Cloud suitabilty? | Enter
| Application List (if DB shared across Applications) | Info
| Cloud suitabilty? | Enter
| DB Clustered | Enter
| DB Throughput | Enter

## BU Details
BUSINESS UNIT QUESTIONNAIRE
General | [5 empty] | Regulatory |  |  | Business Criticality | [6 empty] | Security |  |  |  |  | License |  |  | Stakeholder Details | [6 empty] | Application Details | [13 empty] | Database |  |  |  |  | Others
BU Name | Application Name | Detailed Description | URL | Application Unique ID (Refer: CI from CMDB) | App Life expectancy (Decommisioning Time) | Compliance requirements (PCI DSS, FISMA, SOC, or if "Others"- please specify) | Regulatory requirements - (Limiting data hosting to specific geography) | If Yes for Regulatory, please indicate the limitation | Business Criticality | Application Availability | Application Availability Comments | Does the application have a business continuity plan? | DR Solutions | RPO (hours) | RTO (hours) | Security Requirement | In-transit Data Encryption | Rest Data Encryption | Authorization and Authentication Model | Indicate the security protocol used? | Licensing Limitations for Portability | If there is a licensing portability limitation - Please describe the limitation | Annual User / Data Growth | Application Owner | Application Owner Contacts | Tech Lead | Business Lead | Testing Lead | Security SPOC | DB / Enterprise technology SPOC | Application Type | Technology Stack | Is Application Architecture Documentation Available? | Hardware / OS dependencies | If yes, list Hardware / OS dependencies | Integration points (include upstream & downstream dependency) | List Upstream Dependencies (Application Names) | List Downstream Dependencies (Application Names) | Scalable Architecture | Is the Application Stateless / Stateful | Who provides support for the apps? | Is the app Home built vs. 3rd party | Detail of built - Does the vendor still support the app | Are there any post install config requirements? Provide details | Database Management System (DBMS) | DBMS Version Details | Application List (if DB shared across Applications) | DB Clustered | DB Throughput | Technology Stack | Upstream Transport | Downstream Transprot | Landing Zone Recommendation | ET/Non ET

## Discovery
Plan
Collect on-prem data\inventory by using Azure Migrate

## Readyness Analysis
This will be discussed after Discovery

## Data Repository
This document outlines the data required to assess the application & infrastructure portfolio. A data source must be provided for each of the Required elements below. Please enter the specific data source and element name in the corresponding "Data Source" row. If no data source is available, mention in selecting an appropriate tool to collect it.
Network
Network CIDR
Web Subnet1
App Subnet1
DB Subnet1
Firewall Ports
| Source | Destination

## Migration
Migration Strategy
Migration Approach
Migration Plan (HLD)
Migration Event schedule
Migration Key decisions
Migration Target Operation Module

## Design & Build
LLD - Low Level Design
Test Stratagey
Test Plan
Test Results
Target Cloud Sizing

## Migrate & Validate
Provision environment and License Management
Detailed Migration Planning
Go/No Go decision
Detailed migration plan
Detailed business continuity plan
Detailed business continuity plan guidance
Communication plan
Migrate workload and data
Test plan
Test case results
Sign-off from business owners
Issue log
Lessons learned report
Test automation and validation
Test scripts
Test script template
Test validation reports
Test completion report
User stories
Use case

## Handover and Optimization
Handover and Optimization
Handover to support team
Completed handover to BAU checklist
Incident management report
Problem management report
Management information report
Automated IT management
Optimization scalability
Decommission remaining infrastructure

## Issue Log
ID | Customer Facing (Y/N) | Issue | Date Created | Time Created | Last Modified / Closed Date | Age (in days) | Last Modified / Closed Date | Working Priority | Current Severity | Customer Impact | Status | Owner | Next Steps | Task completion date | Customer Follow Up Required | RCA Required | RCA Completed | Members Involved
1
2
3
4
5
6
7
8
9
10
11
12
13
14

## MOM
Date | Comments
2021-08-17 | Worked on Plan document structure